## Dashboard
Ops2EBITDA
Add-On Synergy Excel Model
Integration value capture dashboard for tuck-in acquisitions and post-close synergy execution.
Gross Synergy Target |  | Net Synergy Target |  | Validated EBITDA |  | Validation % |  | EV Uplift
12590000 |  | 10158800 |  | 2826655 |  | 27.82% |  | 32506532.5
Current Read
Current read: $2.8M of validated EBITDA captured, representing 27.8% of net target. Focus on at-risk workstreams and the largest gaps to target.
Priority Integration Workstreams
Workstream | Initiatives | # At Risk | Net Target ($) | Run-Rate Captured ($) | Validated EBITDA ($) | Validation % | Exit Value ($) | Status | Gap to Target ($) | Management Action
Procurement | 3 | 0 | 2198000 | 622750 | 371862.5 | 16.92% | 4276418.75 | Behind | 1826137.5 | Escalate owner and rebuild recovery plan
Supply Chain / Logistics | 2 | 1 | 1102800 | 444680 | 416470 | 37.76% | 4789405 | Behind | 686330 | Improve evidence and validation
G&A / SG&A | 4 | 0 | 1724000 | 1019700 | 940050 | 54.53% | 10810575 | Behind | 783950 | Monitor
Systems / IT | 3 | 1 | 982500 | 328040 | 285192.5 | 29.03% | 3279713.75 | Behind | 697307.5 | Improve evidence and validation
Facilities / Footprint | 2 | 0 | 746000 | 20800 | 7280 | 0.9759% | 83720 | Behind | 738720 | Improve evidence and validation
Finance / Back Office | 2 | 0 | 691400 | 207680 | 155760 | 22.53% | 1791240 | Behind | 535640 | Improve evidence and validation
Revenue / Cross-sell | 2 | 0 | 1677500 | 147300 | 51555 | 3.073% | 592882.5 | Behind | 1625945 | Escalate owner and rebuild recovery plan
Revenue Leakage | 2 | 0 | 1036600 | 672860 | 598485 | 57.74% | 6882577.5 | Watch | 438115 | Monitor
Value Capture Visualization
Workstream | Net Target ($) | Validated EBITDA ($) | Gap to Target ($) | Validation % | Target Bar | Validated Bar | Gap Bar | Status | Evidence Focus | Owner Action
Procurement | 2198000 | 371862.5 | 1826137.5 | 16.92% | 2198000 | 371862.5 | 1826137.5 | Behind | Low validation | Escalate owner and rebuild recovery plan
Supply Chain / Logistics | 1102800 | 416470 | 686330 | 37.76% | 1102800 | 416470 | 686330 | Behind | Low validation | Improve evidence and validation
G&A / SG&A | 1724000 | 940050 | 783950 | 54.53% | 1724000 | 940050 | 783950 | Behind | Validate evidence | Monitor
Systems / IT | 982500 | 285192.5 | 697307.5 | 29.03% | 982500 | 285192.5 | 697307.5 | Behind | Low validation | Improve evidence and validation
Facilities / Footprint | 746000 | 7280 | 738720 | 0.9759% | 746000 | 7280 | 738720 | Behind | Low validation | Improve evidence and validation
Finance / Back Office | 691400 | 155760 | 535640 | 22.53% | 691400 | 155760 | 535640 | Behind | Low validation | Improve evidence and validation
Revenue / Cross-sell | 1677500 | 51555 | 1625945 | 3.073% | 1677500 | 51555 | 1625945 | Behind | Low validation | Escalate owner and rebuild recovery plan
Revenue Leakage | 1036600 | 598485 | 438115 | 57.74% | 1036600 | 598485 | 438115 | Watch | Validate evidence | Monitor

## Instructions
How to Use This Model
Step | Action | Details | Workbook Flow
1 | Update Inputs | Edit blue-font assumptions in the Inputs sheet. Update close date, current month, multiples, haircut, and financial baselines. | Inputs | Set assumptions and deal baseline
2 | Replace sample synergy initiatives | Use Synergy_Tracker to enter each cost, revenue, systems, footprint, and back-office synergy. Keep one initiative per row. | Target_Financials | Review target cost base and entry economics
3 | Validate one-time costs | Add integration costs by initiative so the EBITDA and value bridge separates run-rate value from implementation cost. | Synergy_Tracker | Enter initiatives, target values, risk haircuts, realization, evidence quality
4 | Track milestones | Use Integration_Milestones to manage Day 1, Day 30, Day 100, Month 6, and Month 12 execution. | Integration_Milestones | Track integration execution and due dates
5 | Review Workstream Detail | Use Workstream_Detail to identify which workstreams are behind plan, under-validated, or at risk. | Workstream_Detail | Summarize target/capture/validation by workstream
6 | Use Dashboard for executive readout | Use Dashboard for board/management discussion: total synergy target, captured run-rate, validated EBITDA, EV uplift, and priority actions. | EBITDA_Bridge | Translate synergies into post-synergy EBITDA and enterprise value
7 | Refresh evidence quality | Validated EBITDA is risk-weighted by evidence quality. Increase evidence quality only when savings are visible in budget, invoices, headcount, contracts, or booked contribution margin. | Dashboard | Use as executive summary and management action page

## Inputs
Ops2EBITDA — Add-On Synergy & Integration Value Capture Model
Editable Assumptions
Assumption | Value | Units / Format | Notes
Platform Revenue | 250000000 | $ | Standalone platform revenue
Platform EBITDA | 37500000 | $ | Standalone platform EBITDA
Target Revenue | 50000000 | $ | Acquired target annual revenue
Target EBITDA | 6500000 | $ | Acquired target standalone EBITDA
Platform Exit Multiple | 11.5 | x | Valuation multiple for value capture
Target Purchase Multiple | 7 | x | Entry multiple paid for target EBITDA
Tax / Leakage Rate | 0% | % | Optional leakage rate for net value
Synergy Realization Haircut | 15% | % | Default risk haircut for savings realization
One-Time Integration Cost Multiple | 1.2 | x | Default one-time cost as multiple of Year 1 gross run-rate synergy
Integration Start Date | 2026-06-01 | date | Expected Day 1 / close date
Current Month | 2026-08-31 | date | Used for status and run-rate tracking
EBITDA Validation Threshold | 0.8 | % | Minimum validated / target threshold for green status
Run-Rate Threshold | 0.6 | % | Minimum run-rate / target threshold for watchlist
Currency | USD | text | Model currency
Workstream Benchmarks / Default Realization Curves
Workstream | Default Owner | Realization Month 3 | Realization Month 6 | Realization Month 12 | Risk Level | Typical Evidence Required
Procurement | CPO / CFO | 25% | 55% | 90% | Medium | Signed vendor contract, invoice proof, purchase order compliance
G&A / SG&A | CFO / COO | 35% | 70% | 100% | Medium | Org changes, eliminated run-rate spend, budget removal
Systems / IT | CIO / Integration Lead | 10% | 35% | 75% | High | System decommissioning, license termination, support cost removal
Revenue / Cross-sell | CRO | 5% | 20% | 55% | High | Booked revenue, retained margin, CRM opportunity proof
Facilities / Footprint | COO | 15% | 45% | 85% | High | Lease exit, utilization evidence, cost baseline
Finance / Back Office | CFO | 25% | 60% | 95% | Medium | Closed process migration, headcount/vendor cost removal
Supply Chain / Logistics | COO / VP Supply Chain | 20% | 50% | 90% | Medium | Carrier rate proof, lane-level savings, freight invoices
Revenue Leakage | CRO / CFO | 20% | 55% | 90% | Medium | Contract compliance, billing correction, invoice proof

## Target_Financials
Target + Platform Financial Baseline
Financial Baseline and Entry Value
Metric | Platform | Target | Combined Pre-Synergy | Formula / Notes
Revenue ($) | 250000000 | 50000000 | 300000000 | Platform + target
EBITDA ($) | 37500000 | 6500000 | 44000000 | Standalone EBITDA
EBITDA Margin | 15% | 13% | 14.67% | EBITDA / Revenue
Purchase Enterprise Value ($) |  | 45500000 |  | Target EBITDA x purchase multiple
Implied Revenue Multiple |  | 0.91 |  | Purchase EV / target revenue
Platform EV at Exit Multiple | 431250000 |  | 506000000 | EBITDA x platform multiple
Standalone Target P&L by Function / Cost Base
Function / Cost Base | Annual Cost / Revenue ($) | % of Target Revenue | Integration Relevance | Primary Synergy Lever | Notes
Direct Materials / COGS | 21000000 | 42% | High | Procurement / supply chain | Vendor terms, commodity rates, volume leverage
Freight & Logistics | 3800000 | 7.6% | High | Supply Chain / Logistics | Carrier consolidation and lane optimization
Sales & Marketing | 6500000 | 13% | Medium | G&A / Revenue | Channel overlap, cross-sell, marketing stack
G&A Payroll | 7200000 | 14.4% | High | G&A / SG&A | Duplicative finance, HR, admin roles
IT Software & Infrastructure | 2400000 | 4.8% | High | Systems / IT | Duplicate systems, licenses, hosting, support
Facilities & Occupancy | 3100000 | 6.2% | Medium | Facilities / Footprint | Lease overlap and site consolidation
Finance / Back Office Services | 1800000 | 3.6% | High | Finance / Back Office | External accounting, payroll, AP processing
Other OpEx | 3700000 | 7.4% | Medium | G&A / SG&A | Professional services and discretionary spend

## Synergy_Tracker
Synergy Tracker — Cost, Revenue, and Integration Value Capture
ID | Workstream | Initiative | Owner | Status | Priority | Start Date | Target Date | Gross Target ($) | Risk Haircut % | Net Target ($) | One-Time Cost ($) | Month 3 Realization % | Month 6 Realization % | Month 12 Realization % | Current Realization % | Run-Rate Captured ($) | Validated EBITDA ($) | Evidence Quality | Value at Exit ($) | Notes
SYN-001 | Procurement | Consolidate packaging vendors | CPO | In Progress | High | 2026-06-10 | 2026-10-31 | 950000 | 10% | 855000 | 180000 | 25% | 55% | 95% | 45% | 384750 | 288562.5 | Medium | 3318468.75 | Move target volume to platform preferred supplier
SYN-002 | Procurement | Renegotiate raw material contracts | CPO | Not Started | High | 2026-07-01 | 2026-12-15 | 1400000 | 15% | 1190000 | 220000 | 10% | 45% | 90% | 20% | 238000 | 83300 | Low | 957950 | RFP required for top three suppliers
SYN-003 | Supply Chain / Logistics | Move freight to platform carrier rates | VP Supply Chain | In Progress | High | 2026-06-15 | 2026-09-30 | 760000 | 12% | 668800 | 120000 | 35% | 70% | 95% | 60% | 401280 | 401280 | High | 4614720 | Lane-level validation started
SYN-004 | G&A / SG&A | Eliminate duplicate accounting roles | CFO | Complete | High | 2026-06-01 | 2026-08-31 | 820000 | 5% | 779000 | 410000 | 50% | 85% | 100% | 90% | 701100 | 701100 | High | 8062650 | Severance included in one-time cost
SYN-005 | G&A / SG&A | Consolidate HR and payroll admin | CHRO | In Progress | Medium | 2026-06-20 | 2026-11-30 | 430000 | 10% | 387000 | 160000 | 20% | 55% | 95% | 35% | 135450 | 101587.5 | Medium | 1168256.25 | Transition services period through Q4
SYN-006 | Systems / IT | Decommission target ERP licenses | CIO | At Risk | High | 2026-06-01 | 2027-03-31 | 650000 | 25% | 487500 | 780000 | 0% | 25% | 75% | 10% | 48750 | 17062.5 | Low | 196218.75 | Migration dependencies delaying savings
SYN-007 | Systems / IT | Consolidate CRM and marketing tools | CIO | In Progress | Medium | 2026-07-15 | 2027-01-31 | 310000 | 20% | 248000 | 250000 | 5% | 30% | 80% | 18% | 44640 | 33480 | Medium | 385020 | Includes license rationalization
SYN-008 | Facilities / Footprint | Close duplicate regional office | COO | Not Started | Medium | 2026-08-01 | 2027-02-28 | 520000 | 20% | 416000 | 620000 | 0% | 20% | 85% | 5% | 20800 | 7280 | Low | 83720 | Lease termination negotiation pending
SYN-009 | Finance / Back Office | Move AP to platform shared service | CFO | In Progress | High | 2026-06-20 | 2026-12-31 | 590000 | 12% | 519200 | 240000 | 20% | 55% | 95% | 40% | 207680 | 155760 | Medium | 1791240 | PO compliance required
SYN-010 | Revenue / Cross-sell | Cross-sell target product into platform top accounts | CRO | In Progress | High | 2026-07-01 | 2027-06-30 | 1750000 | 35% | 1137500 | 300000 | 5% | 20% | 55% | 12% | 136500 | 47775 | Low | 549412.5 | Contribution margin savings equivalent
SYN-011 | Revenue / Cross-sell | Bundle platform service into target accounts | CRO | Not Started | Medium | 2026-09-01 | 2027-09-30 | 900000 | 40% | 540000 | 180000 | 0% | 10% | 45% | 2% | 10800 | 3780 | Low | 43470 | Requires sales enablement
SYN-012 | Revenue Leakage | Correct under-billed service fees | CFO / CRO | Complete | High | 2026-06-05 | 2026-08-15 | 480000 | 8% | 441600 | 40000 | 50% | 85% | 100% | 85% | 375360 | 375360 | High | 4316640 | Contract-to-invoice audit complete
SYN-013 | G&A / SG&A | Professional services vendor rationalization | CFO | In Progress | Medium | 2026-07-01 | 2026-11-15 | 350000 | 10% | 315000 | 30000 | 20% | 55% | 95% | 35% | 110250 | 82687.5 | Medium | 950906.25 | Outside counsel/accounting overlap
SYN-014 | Procurement | IT hardware and telecom contract rebid | CIO / CPO | Not Started | Low | 2026-08-15 | 2027-01-15 | 180000 | 15% | 153000 | 25000 | 0% | 35% | 90% | 0% | 0 | 0 | Low | 0 | Tail opportunity
SYN-015 | Supply Chain / Logistics | Standardize warehouse labor model | COO | At Risk | Medium | 2026-07-01 | 2027-02-28 | 620000 | 30% | 434000 | 280000 | 5% | 30% | 75% | 10% | 43400 | 15190 | Low | 174685 | Labor relations risk
SYN-016 | Finance / Back Office | Outsource/automate expense processing | CFO | Not Started | Low | 2026-10-01 | 2027-04-30 | 210000 | 18% | 172200 | 90000 | 0% | 20% | 80% | 0% | 0 | 0 | Low | 0 | Could bundle with AP migration
SYN-017 | Systems / IT | Terminate duplicate cyber and endpoint tools | CIO | Complete | Medium | 2026-06-01 | 2026-09-01 | 260000 | 5% | 247000 | 15000 | 35% | 75% | 100% | 95% | 234650 | 234650 | High | 2698475 | Termination letters confirmed
SYN-018 | Revenue Leakage | Harmonize surcharge pass-through policy | CFO / CRO | In Progress | High | 2026-06-15 | 2026-10-15 | 700000 | 15% | 595000 | 50000 | 30% | 70% | 95% | 50% | 297500 | 223125 | Medium | 2565937.5 | Requires sales comp alignment
SYN-019 | Facilities / Footprint | Consolidate warehouse overflow space | COO | Not Started | Medium | 2026-09-01 | 2027-05-31 | 440000 | 25% | 330000 | 380000 | 0% | 15% | 75% | 0% | 0 | 0 | Low | 0 | Inventory cleanup dependency
SYN-020 | G&A / SG&A | Insurance broker consolidation | CFO | In Progress | Low | 2026-07-15 | 2026-12-15 | 270000 | 10% | 243000 | 20000 | 10% | 50% | 95% | 30% | 72900 | 54675 | Medium | 628762.5 | Benchmark underway

## Integration_Milestones
Integration Milestones — Day 1 to Day 365 Execution Control
Milestone ID | Phase | Workstream | Milestone | Owner | Due Date | Status | Dependency | Criticality | Days Until Due | Late? | Notes
M-001 | Day 1 | Finance / Back Office | Open combined cash reporting process | CFO | 2026-06-01 | Complete | Close | High | -91 |  | Day-1 treasury visibility
M-002 | Day 1 | Management Cadence | Launch integration command center | Integration Lead | 2026-06-03 | Complete | Close | High | -89 |  | Weekly integration review
M-003 | Day 30 | G&A / SG&A | Confirm duplicate role list and severance plan | CFO / CHRO | 2026-06-30 | Complete | HR diligence | High | -62 |  | Needed for run-rate validation
M-004 | Day 30 | Procurement | Load target vendor master into spend cube | CPO | 2026-06-30 | Complete | AP extract | High | -62 |  | Supports quick-win sourcing
M-005 | Day 60 | Revenue Leakage | Complete contract-to-invoice audit | CFO / CRO | 2026-07-31 | Complete | Customer contracts | High | -31 |  | Billing correction workstream
M-006 | Day 60 | Systems / IT | Finalize target ERP migration plan | CIO | 2026-07-31 | In Progress | Data mapping | High | -31 | Late | Delay risk
M-007 | Day 90 | Supply Chain / Logistics | Move freight lanes to platform carriers | VP Supply Chain | 2026-08-31 | In Progress | Carrier contracts | High | 0 |  | Track lane-level compliance
M-008 | Day 90 | Finance / Back Office | Move AP approval workflow to platform standard | CFO | 2026-08-31 | In Progress | PO policy | Medium | 0 |  | Shared service dependency
M-009 | Day 100 | Board / Governance | Approve updated synergy forecast | Integration Lead | 2026-09-08 | Not Started | Validated tracker | High | 8 |  | Board decision point
M-010 | Month 6 | Procurement | Complete top 10 supplier renegotiations | CPO | 2026-11-30 | Not Started | RFP launch | High | 91 |  | Large cost synergy
M-011 | Month 6 | Sales / Revenue | Launch cross-sell playbook with top 50 accounts | CRO | 2026-11-30 | In Progress | Sales enablement | High | 91 |  | Requires account mapping
M-012 | Month 6 | G&A / SG&A | Remove duplicated budget from FY27 plan | CFO | 2026-12-15 | Not Started | Budget cycle | High | 106 |  | Proof of EBITDA capture
M-013 | Month 9 | Systems / IT | Migrate core financial data to platform ERP | CIO | 2027-02-28 | At Risk | ERP migration plan | High | 181 |  | At-risk dependency for license savings
M-014 | Month 9 | Facilities / Footprint | Negotiate regional office lease exit | COO | 2027-02-28 | Not Started | Legal review | Medium | 181 |  | Landlord discussion needed
M-015 | Month 12 | Systems / IT | Decommission target ERP | CIO | 2027-05-31 | Not Started | ERP migration | High | 273 |  | Unlocks IT savings
M-016 | Month 12 | Revenue / Cross-sell | Validate first-year cross-sell contribution margin | CRO / CFO | 2027-05-31 | Not Started | Booked revenue | High | 273 |  | Revenue synergy proof
M-017 | Month 12 | Integration Office | Close integration office or transition to BAU owners | Integration Lead | 2027-06-30 | Not Started | All workstreams | Medium | 303 |  | Institutionalize tracking

## Workstream_Detail
Workstream Detail — Target, Capture, Validation, and Status
Workstream | Initiatives | # Complete | # At Risk | Gross Target ($) | Net Target ($) | Run-Rate Captured ($) | Validated EBITDA ($) | Validation % | Exit Value ($) | Status
Procurement | 3 | 0 | 0 | 2530000 | 2198000 | 622750 | 371862.5 | 16.92% | 4276418.75 | Behind
Supply Chain / Logistics | 2 | 0 | 1 | 1380000 | 1102800 | 444680 | 416470 | 37.76% | 4789405 | Behind
G&A / SG&A | 4 | 1 | 0 | 1870000 | 1724000 | 1019700 | 940050 | 54.53% | 10810575 | Behind
Systems / IT | 3 | 1 | 1 | 1220000 | 982500 | 328040 | 285192.5 | 29.03% | 3279713.75 | Behind
Facilities / Footprint | 2 | 0 | 0 | 960000 | 746000 | 20800 | 7280 | 0.9759% | 83720 | Behind
Finance / Back Office | 2 | 0 | 0 | 800000 | 691400 | 207680 | 155760 | 22.53% | 1791240 | Behind
Revenue / Cross-sell | 2 | 0 | 0 | 2650000 | 1677500 | 147300 | 51555 | 3.073% | 592882.5 | Behind
Revenue Leakage | 2 | 1 | 0 | 1180000 | 1036600 | 672860 | 598485 | 57.74% | 6882577.5 | Watch
Total | 20 | 3 | 2 | 12590000 | 10158800 | 3463810 | 2826655 | 27.82% | 32506532.5 | Watch

## EBITDA_Bridge
EBITDA Bridge — Standalone to Post-Synergy Run-Rate
Bridge Summary
Bridge Item | Amount ($) | Notes
Platform Standalone EBITDA | 37500000 | From Inputs
Target Standalone EBITDA | 6500000 | From Inputs
Combined Pre-Synergy EBITDA | 44000000 | Platform + target
Validated Cost Synergies | 2775100 | Validated non-revenue synergies
Validated Revenue Synergy Contribution | 51555 | Revenue synergy contribution margin equivalent
Post-Synergy Run-Rate EBITDA | 46826655 | Current validated run-rate
Incremental EBITDA vs. Pre-Synergy | 2826655 | Value capture
One-Time Integration Costs | 4390000 | Estimated one-time cost
Enterprise Value Uplift | 32506532.5 | Incremental EBITDA x exit multiple
Net Value After One-Time Costs | 28116532.5 | EV uplift less one-time integration costs
Value Capture by Workstream
Workstream | Net Target ($) | Validated EBITDA ($) | Gap to Target ($) | Validation % | Exit Value ($)
Procurement | 2198000 | 371862.5 | 1826137.5 | 16.92% | 4276418.75
Supply Chain / Logistics | 1102800 | 416470 | 686330 | 37.76% | 4789405
G&A / SG&A | 1724000 | 940050 | 783950 | 54.53% | 10810575
Systems / IT | 982500 | 285192.5 | 697307.5 | 29.03% | 3279713.75
Facilities / Footprint | 746000 | 7280 | 738720 | 0.9759% | 83720
Finance / Back Office | 691400 | 155760 | 535640 | 22.53% | 1791240
Revenue / Cross-sell | 1677500 | 51555 | 1625945 | 3.073% | 592882.5
Revenue Leakage | 1036600 | 598485 | 438115 | 57.74% | 6882577.5
Total | 10158800 | 2826655 | 7332145 | 27.82% | 32506532.5